## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-05-A"
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | SF 9/30/21; works as intended
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | SF 9/30/21; works as intended
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | SF 9/30/21; this part works as intended, related problem detailed in next test parameter
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | SF 9/30/21; does not allow the use of spaces at all MS 10/1/21; does not allow the use of spaces at all
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | SF 9/30/21; works as intended
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | SF 9/30/21; works as intended, but does not update EXACTLY in real time, there is a very short delay between whenever someone signs on or off, and when the page reloads. This could pose problems for matchmaking.
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | SF 9/30/21; works as intended, updates somewhat in real time. Reloads page every few seconds so may not be accurate in a short period of time.
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | ZM 10/2/21; works as intended
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | ZM 10/2/21; works as intended
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | ZM 10/2/21; works as intended
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | ZM 10/2/21; works as intended
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | ZM 10/2/21; works as intended
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | ZM 10/2/21; works as intended
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | ZM 10/2/21; works as intended
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | ZM 10/2/21; works as intended
As a player I want to have a signout option so that I can either change my name or stop playing | **Given** that I am signed in **when** I reach the homepage **then** I should see a sign out option | Pass | MK 10/25/21; works as intended
| **Given** that I'm signed in **when** I click the sign out option **then** I should be redirected to the homepage as a new user | Pass | MK 10/25/21; works as intended
As a player I want to make a simple move so that I can move away or get closer to a chip. | **Given** that I am in a game **when** I click and drag my piece to a valid space **then** my piece should move to that space. | Pass | MK 10/25/21; works as intended
| **Given** that it is my turn **when** I try to make a move that is further than one diagonal space away and is not a jump move **then** my piece should NOT be allowed to move to that spot. | Pass | MK 10/25/21;
| **Given** that the piece I want to move is a single (not a king) **when** I attempt to move it in any backwards direction **then** my piece should NOT be allowed to move there. | Pass | MK 10/25/21; works as intended
As a player I want to be able to resign so that end a game early. | **Given** A game is currently being played **when** Click the forfeit button **then** I expect the game to end regardless of if it is my turn. | Pass | MK 10/25/21; works as intended
| **Given** The player I am facing has resigned **when** the game ends **then** I expect to see that I won the game. | Pass | MK 10/25/21; works as intended
| **Given** I have resigned from a game **when** the game ends **then** I expect to see that I lost the game. | Pass | MK 10/25/21; works as intended
As a player I want to see that game is over so that I can win or lose the game. | **Given** the game is running, **when** I eliminate the enemy's last piece **then** I expect the game to end in a win. | Pass | MK 10/25/21; works as intended
| **Given** the game is running, **when** the enemy eliminates my last piece **then** I expect the game to end in a loss. | Pass | MK 10/25/21; works as intended
| **Given** the game is running and no victor has been declared, **when** I or my enemy resign **then** I expect the game to end in a loss for the quitter. | Pass | MK 10/25/21; works as intended
As a player I want to make a single jump move so that I can defeat one chip. | Given there is an empty space diagonally across from an adjancent piece in front of me, when I attempt to move to that space then I should jump over that piece. | Pass | MK 10/25/21; works as intended
| Given there is an empty space diagonally across from an adjancent piece in front of me, when I jump over that piece, then piece should be removed from the board. | Pass | MK 10/25/21; works as intended
| Given there is a piece forward and adjacent to me and a piece forward and adjacent to it, when I try to jump that piece, then I should not be able to. | Pass | MK 10/25/21; works as intended
As a player want to know who is next so that my opponent does not go two times in a row. | **Given** that it's my turn **when** I submit my move **then** it should no longer be my turn. | Pass | MK 10/25/21; works as intended
As a Player, I want to jump over multiple of my opponent’s pieces a diagonal space away so that I can get rid of as many of my opponent’s pieces as possible | **Given** that i can make a valid diagonal **when** it is my turn **then** I expect to take multiple jumps | Pass | MK 10/25/21; works as intended, player needs to palce pieces on each square, not go directly to the intended space.
| **Given** that there are no other jumpable opponent pieces **when** I've already jumped one piece **then** I should NOT be able to move again | Pass | MK 10/25/21;
| **Given** that I am not yet a king **when** it is my turn **then** should only be able to take multiple jumps forward | Pass | MK 10/25/21; works as intended
As a player I want to be able to undo my last move so that I make a different move. | **Given** that I made a move **when** click "Backup" **then** my move should be reversed. | Pass | MK 10/25/21; works as intended
As a player I want to turn a chip into a king so that I can have more abilities. | Given my piece is a single piece when I reach it reaches the last row on the board then my piece should become a king. | Pass | MK 10/25/21; works as intended
| Given my piece is a king piece, when I move that piece in any direction to a valid space, then the move should be accepted. | Pass | MK 10/25/21; works as intended
| Given my piece is a king piece, when I move away from the final row then my piece should remain a king for the duration of the game. | Pass | MK 10/25/21; works as intended
As a player I want to have a comparable winrate so that I can be matched with similarly skilled players. | **Given** that I have played a game **when** I reach the homepage **then** my winrate should appear. | Pass | MK 10/25/21; works as intended
As a player if I Have no valid movement options the game should end. | Given that my opponent cannot move another valid move then I shall win that game. | Pass | MK 10/25/21; works as intended
| Given that I can no longer make a valid move my opponent will win | Pass | MK 10/25/21; works as intended
| Given that I have won when player can no longer move then I shall be redirected to the home page. | Pass | MK 10/25/21; works as intended
As a player I want to be forced to take an available jump so that I ensure the rules of American chekers are being followed | given there was an available jump at the start of my turn when I submit a simple move(non-jump) then the turn should not be valid and the sumbit should fail.
**Given** there is another available jump AFTER my first jump **when** I attempt to submit the turn **then** the turn should NOT be valid and the SUBMIT should fail.
As a Tournament Orgranizer I want to be able to create a tournament so that players can join it. | given I signed in when I see the homepage then I should be able to create a tournament | [6 empty] | Pass | mck 11/7
| given I signed in hen I receive a tournament invite then I should be able to join the tournament | [6 empty] | Pass | mck 11/7
As a Player I want to see my statistics so that I know my standings as well as my win/lose ratio compared to other players in my tournament | **Given** that any players username is on the screen **when** I am logged into the homepage or a tournament **then** I should see those players statitics next to their name. | [6 empty] | Pass | mck 11/7
As a player I want to be able to see my achievements | Given that I have beat an AI then I will receive that badge next to my name
As a player I want to start my tournament so that I can begin playing in the tournament | Given that all the players that I need to play a tournament are ready, the the tournament should automatically start. | [6 empty] | Pass | mck11/7
As a Player, I want to be able to view the current bracket of the tournament | Given that I am signed in I should be able to see which player is playing with who. | [6 empty] | Pass | mck 11/7
| Given that I am in a tournament, then I should be able to see the bracket for future games in the tournament. | [6 empty] | Pass | mck 11/7
Once the tournament starts, I want all players to be matched up automatically | Given that I am in a tournament, I should be randomly assigned to another online player in the tournament. | [6 empty] | Pass | mck 11/7
As a player I want to start a game with an AI so that I can play alone or practice. | **Given** that I'm signed in **when** I see the homepage **then** AI game should be an option. | [6 empty] | Pass | Mss 11/11
| **Given** that I'm signed in **when** I click "Versus AI" **then** A game should immediately begin against the server. | [6 empty] | Pass | Mss 11/11
As an AI I want to make an intentional ove that will base the moves off of the current player | AI will be able to calculate strategic move | [6 empty] | Pass | Mss 11/11
As a player I want to be able to choose what level of AI I will be fighting | Given that I am signed, I should be able to see the option to play with the AI | [6 empty] | Pass | Mss 11/11
| Given that I a ready to play a game, the AI can be chosen from the list of online players. Three levels of difficutly should be shown. | [6 empty] | Pass | Mss 11/11